## Sheet1
ID | Category | Page / Location | Issue Type | Severity | Description | Evidence | Suggested Fix | Status | Resolution & Engineering Notes
1 | Performance | Site-Wide | Blank Screen on Page Load | CRITICAL | Every product and solution page renders a fully blank dark screen for 3-5 seconds on arrival. No skeleton states or SSR. The site is a heavy client-side SPA. | Observed on every page navigation during audit | Add SSR/SSG or skeleton loading screens. Defer non-critical scripts. Lazy-load animations. Implement route-level code splitting. | Fixed | Root cause was NOT 'no SSR' — the root layout is a server component. useSearchParams() in PostHogProvider + LocaleSwitcher bailed the site-wide <Suspense fallback=null> out of SSR, so the server shipped a blank dark body. Isolated both consumers and removed the blanket Suspense. Every route now server-renders content (verified: 177KB SSR HTML). sundae-website PR #90 (merged to main, live on sundae.io)
2 | Performance | Site-Wide | RAM / Bundle Size Too Heavy | HIGH | Site is RAM-heavy (user-reported). Likely caused by WebGL backgrounds, unoptimised video assets, and a monolithic JS bundle loaded upfront on every route. | User-reported + slow loads across all pages | Run Lighthouse audit. Tree-shake unused libraries. Compress and lazy-load video. Move decorative animations to CSS. | Fixed (partial) | Added experimental.optimizePackageImports (framer-motion, lucide-react). NOTE: the auditor's WebGL/video causes were WRONG — the one WebGL scene is homepage-only + dynamic(ssr:false) + IntersectionObserver-gated; the 2 videos are homepage-only, preload='none' + poster, <=1.9MB. Real lever was the framer-motion barrel. Full bundle delta not yet measured with an analyzer. sundae-website PR #90 (merged to main, live on sundae.io)
3 | Bug - UX | Site-Wide | Cookie Banner Not Persisted Across Pages | HIGH | The cookie consent banner reappears on every page navigation despite having already been accepted or declined. Preference is not being stored or read correctly. | Banner reappeared fresh on Pulse / Benchmarking / Watchtower / Insights / Intelligence / Foresight / Crew / Solutions / About / Security / Careers pages | Store consent decision in localStorage or a persistent cookie on first interaction. Read the value on every subsequent page before rendering the banner. | Fixed | Consent WAS persisted (localStorage); the 'reappearing' was a pre-hydration flash on hard loads (getServerSnapshot returned null). Now mirrored to a cookie so the server seeds the initial state -> no flash. 22 locales. sundae-website PR #90 (merged to main, live on sundae.io)
4 | Bug - CRITICAL | /solutions/multi-location-groups | Cookie Decline Button Misfires Page Navigation | CRITICAL | Clicking Decline on the cookie banner on the multi-location groups solution page triggered a full page redirect to /demo. A consent button must never redirect the user. | Clicking Decline sent browser to https://www.sundae.io/demo | Inspect event listener on Decline for this page. Likely a z-index overlay issue where the consent button click also fires an underlying CTA. Fix event propagation and z-index stacking. | Not valid | CRITICAL but could NOT reproduce. Decline is a <button> at z-[9999] whose handler only writes localStorage; the multi-location-groups layout is a pure metadata wrapper with no /demo link, overlay, or onClick. No code path exists for the reported redirect — the stated z-index-overlay cause is contradicted by the code. Most likely an automated-click misfire during the crawl. No change (recommend a manual re-test to close).
5 | Bug - SEO | Benchmarking / Insights / Intelligence / Foresight / Crew / Security / Careers / Blog / Report-vs-Core | Missing Unique Page Title Tags | MEDIUM | 8+ pages share the generic title Sundae - Decision Intelligence for Restaurants. Only Pulse and Multi-Location Groups pages had correct unique page titles. Harms SEO and browser tab clarity. | Tab titles on screenshots during audit | Assign every page a unique descriptive title tag. E.g. Sundae Foresight - Predictive Intelligence or Sundae Insights - 12 Analytics Modules. | Fixed | Auditor's 'only Pulse + Multi-Location have titles' was STALE (a prior fix had already added the solutions titles). Real issue was broader: ~36 routes shared the generic title. Root-cause fix: a central pageTitles map resolved in the root-layout generateMetadata (pages with their own title still override). 34 routes titled; English + 21-locale transcreation. Verified live. sundae-website PR #90 (merged to main, live on sundae.io)
6 | Inconsistency | Main Nav vs Footer | Nav Labels Differ From Footer Labels for Same Pages | MEDIUM | The nav menu uses abbreviated labels (e.g. Benchmarks) but the footer uses full labels (e.g. no differentiation). More critically the nav says Security and Compliance while the footer says Security and Compliance - these match but the nav groups items differently to the footer making it hard to cross-reference. | Hamburger nav menu vs footer columns observed during audit | Unify the naming and grouping of navigation items between the hamburger menu and the footer. Users scanning both should see identical labels for the same destinations. | Not valid | The footer reads from the SAME nav.* i18n source as the navbar (shared by construction), so labels cannot diverge. The finding text is also internally self-contradictory. No change.
7 | Inconsistency | Pricing Page vs Main Site | Pricing Subdomain Has Completely Different Visual Design | HIGH | Pricing lives at pricing.sundae.io with a different header style - white/light background option, light/dark mode toggle, different font scale, no hamburger menu. Feels like a separate product website at the highest-intent funnel moment. | Screenshot of pricing.sundae.io vs main site screenshots | Migrate pricing to www.sundae.io/pricing using the main site design system. Or at minimum match the pricing subdomain header and footer exactly to the main site. | Fixed | Pricing subdomain chrome realigned (separate sundae-pricing repo): footer rebuilt to mirror the marketing footer (brand lockup + tagline + X/LinkedIn/YouTube social + link nav + legal bar); header polished to the glassy navbar treatment. Tokens/fonts/coral-S logo were already harmonized in prior brand work. Kept AS a subdomain (a deliberate Jan-2026 redirect) rather than migrating to /pricing. sundae-pricing PR #18 (merged to main, deploying to pricing.sundae.io)
8 | Inconsistency | Sign-In Page vs App | App Domain is Different to Marketing Domain | HIGH | Marketing site is sundae.io. The app login redirects to app.sundaetech.ai - a completely different domain. No in-product branding explains this. Users expect app.sundae.io. | Sign-in page shows explicit redirect to app.sundaetech.ai | Consolidate to app.sundae.io if possible. If not, add a prominent trust note on the sign-in page explaining the redirect with brand reassurance. | Fixed (mitigation) | Confirmed: APP_URL = app.sundaetech.ai differs from sundae.io. Added a security trust note on the sign-in bridge explaining the official app domain (21 locales). Full consolidation to app.sundae.io is an infra roadmap item (not done). sundae-website PR #90 (merged to main, live on sundae.io)
9 | Security | Sign-In Flow | Different App Domain Creates Phishing Attack Surface | HIGH | The sundae.io vs app.sundaetech.ai domain split is a known phishing attack vector. Bad actors can register lookalike domains and intercept credentials from users already conditioned to log in on a different domain. | Sign-in page redirect observed during audit | Consolidate to single domain family. Implement HSTS preloading on the app domain. If domain change is not short-term viable add domain verification messaging on the sign-in bridge page. | Fixed (mitigation) | 'Phishing vector' framing is overstated, but the cross-root-domain jump is a real trust concern. Mitigation shipped: sign-in trust note (row 8) + HSTS/preload already present on the marketing site (next.config.ts). Domain consolidation = roadmap. sundae-website PR #90 (merged to main, live on sundae.io)
10 | Inconsistency | Cookie Banner - Main Site vs Pricing Subdomain | Main Site Cookie Banner Missing Privacy Policy Link | MEDIUM | The main sundae.io cookie banner has no Privacy Policy link. The pricing.sundae.io banner does include one. Inconsistent and non-compliant with GDPR/PECR on the main site. | Main site banner vs pricing subdomain banner | Add a Privacy Policy link to the main site cookie banner matching the pricing subdomain version. | Fixed | Confirmed missing. Added a localized Privacy Policy link (-> /privacy) to the cookie banner. 22 locales. sundae-website PR #90 (merged to main, live on sundae.io)
11 | Inconsistency | Footer vs Nav - No Light/Dark Parity | No Light Mode on Main Site - Inconsistent with Pricing Subdomain | LOW | Main site is dark-mode only. Pricing subdomain has a light/dark toggle. These should be consistent across all Sundae web properties. | Pricing subdomain has toggle. Main site does not. | Decide: either add light/dark toggle to main site or remove it from pricing subdomain. Commit to one brand position. | Not valid | Stale/incorrect: the main site DOES have a light/dark ThemeToggle (rendered in the Navbar on desktop + mobile) with full ThemeProvider light-mode support + persistence. Not dark-only. No change.
12 | Inconsistency | Report vs Core Page vs Breadcrumb | Breadcrumb Shows Report Vs Core - Capitalised Incorrectly | LOW | The breadcrumb on the Report vs Core page reads Report Vs Core with capital V. Should read Report vs Core with lowercase vs to match standard copywriting convention used elsewhere on the site. | Breadcrumb visible on /report-vs-core page | Update breadcrumb component to use lowercase vs consistently. Audit all breadcrumbs across the site for capitalisation consistency. | Fixed | Exact root cause found: formatSegment() title-cased every hyphen-split word and there was no 'report-vs-core' label override -> 'Report Vs Core'. Fixed the formatter to keep minor words (vs/and/or/of/to...) lowercase — fixes the whole class, all locales. sundae-website PR #90 (merged to main, live on sundae.io)
13 | Bug - Broken | Footer - Resources column | Free Tools and Calculators Has No Link | MEDIUM | In the footer Resources column Free Tools and Calculators is plain unlinked text. Every other footer item is a clickable link. This is an unfinished feature or forgotten href attribute. | Footer visible on homepage and all inner pages | Add correct destination URL or remove item from footer until the page is ready. | Not valid | It works: 'Free Tools & Calculators' is a tracked CTA <button> that router.push-es to /tools (via useCta). NOT 'unlinked text / forgotten href'. Optional a11y/SEO nicety (render as an <a> for middle-click/crawlability) noted, but it is not broken. No change.
14 | Bug - Copy | /crew | Grammatically Broken Sentence in Hero | MEDIUM | Crew hero contains: a loop standalone HR or payroll vendors cannot close. Syntactically broken. The word loop is unconnected and meaning is unclear. | Crew page hero text | Rewrite to: a closed-loop that standalone HR or payroll vendors cannot replicate. Run full copy review on Crew page. | Fixed | Awkward but not 'broken' — an omitted-'that' contact clause. Inserted 'that': '...a loop that standalone HR or payroll vendors cannot close.' NOTE: the auditor's rewrite ('cannot replicate') would have broken the page's own 'close the loop' metaphor. The 21 non-EN locales already read correctly (verified) — English-only fix. sundae-website PR #90 (merged to main, live on sundae.io)
15 | UX - Navigation | Site-Wide | Desktop Uses Hamburger-Only Navigation | MEDIUM | No persistent top nav bar on desktop. All navigation is hidden behind a hamburger icon top-right. Forces an extra click to explore the product and reduces discoverability for new visitors. | All screenshots during audit - hamburger only on every page | Add a persistent horizontal nav bar on desktop (1024px+). Reserve hamburger for mobile only. | Left (intentional) | Partly incorrect: a full desktop mega-menu nav DOES exist, gated at the xl breakpoint (>=1280px). Only 1024-1279px sees hamburger-only. Kept (defensible — tight CTA spacing at narrow widths). Could lower to lg (1024px) in a later pass.
16 | UX - Navigation | Site-Wide | No Global Search | LOW | Site has 6 product modules, 5 Crew modules, 10 solution pages, 64 blog articles, and an extensive FAQ. No search bar exists anywhere on the site. | No search element found on any page during audit | Add global search (CMD+K or visible icon) that covers pages, blog, FAQ, and integrations. | Deferred | Valid: no global search exists. Low priority for a marketing site (a product decision). Not done this pass.
17 | UX - Navigation | Product and Solution Pages | No Sticky Nav or Back-to-Top on Inner Pages | LOW | Pages are very long. Homepage has a right-side dot navigator but this disappears on all inner pages. No sticky nav, no floating CTA, no back-to-top button on deep pages. | Dot nav present on homepage only. Absent on all product/solution pages. | Add sticky top nav or floating back-to-top button on all pages longer than 3 viewports. Consider a floating Book a Demo CTA appearing after 50% scroll depth. | Deferred | Partly valid: the top nav IS already sticky/fixed. A back-to-top / floating CTA on long pages is a reasonable minor enhancement — deferred (low priority).
18 | Inconsistency | Homepage Hero vs Inner Page Heroes | Hero Copy Tone Inconsistent - Brand vs Product | MEDIUM | The homepage hero is evocative and narrative (Every plate every cover every shift is a decision). Product page heroes are punchy and metric-led ($2K Lost Per Bad Shift). Watchtower hero is question-led (10+ Competitors Tracked Daily). These tones vary significantly without a clear system. | Homepage hero vs Pulse hero vs Watchtower hero vs Benchmarking hero | Define a hero copywriting framework: decide whether the brand voice is narrative, punchy/metric, or question-led and apply consistently across all page heroes. | Left (intentional) | Tone variance (narrative brand hero vs metric-led product/conversion heroes) is an intentional design choice, not a defect. Optional to systematize into a framework; left as-is.
19 | UX - Flow | Homepage | Product Category Not Obvious in First Viewport | MEDIUM | Hero headline Every plate every cover every shift is a decision is evocative but does not identify Sundae as software, AI platform, or analytics tool. First-time visitors must scroll 2-3 sections to understand the product category. | Homepage first viewport screenshot | Add a one-liner directly in the first viewport: e.g. The AI operating platform for multi-location restaurants. Make category clear before the scroll. | Fixed | The FIRST hero ALREADY stated the category (eyebrow 'Decision intelligence for multi-location operators') — the auditor conflated a later poetic beat ('Every plate...') with the hero. Sharpened the eyebrow to name it as a platform: 'The decision-intelligence platform for multi-location operators' — kept industry-agnostic (not 'restaurants') per founder. 22 locales. Live. sundae-website PR #90 (merged to main, live on sundae.io)
20 | UX - Content | Site-Wide | No Named Customer Logos or Validated Case Studies | HIGH | Site explicitly states: Named pilot results and validated customer outcomes will replace this section as they become available. This weakens social proof significantly for enterprise buyers. | Homepage industry observations disclaimer | Prioritise 2-3 named beta customer quotes with a quantified outcome. One real logo and metric outperforms 10 feature sections for enterprise conversion. | Left (business action) | Valid conversion concern, but the 'no named customers' state is an INTENTIONAL, honest pre-pilot disclaimer (we won't fabricate logos/quotes). Resolving it is a business action — land a named pilot + get attribution — not a code fix.
21 | UX - Content | Site-Wide | Text-Heavy Sections on Multiple Pages | MEDIUM | Insights page lists all 12 modules in text. Homepage has 6+ consecutive text-heavy sections. Dense for time-poor restaurant operators who scan rather than read. | Insights page and homepage lower sections | Replace text-heavy module lists with icon + 2-line card format. Use annotated product screenshots instead of long paragraphs. Target: no single body text block exceeding 3 lines. | Deferred | Editorial judgment. Some density exists, but many sections are already card/visual-based. Page-by-page copy tightening deferred (low priority; not a bug).
22 | UX - Content | Site-Wide | Overuse of AI and Product Jargon | MEDIUM | Terms like Decision Intelligence, Six Layers, Governed Schema, Source-cited AI, Watchtower, 4D Intelligence Model stack up across pages. Abstract for non-technical operators - GMs, owners, area managers. | Site-wide copy on all product and solution pages | Add plain-English sub-descriptions alongside branded terms. E.g. Sundae Intelligence (ask your data a question and get an instant cited answer). Add tooltip or explainer for any non-obvious term. | Left (intentional) | Brand terms (Decision Intelligence, Watchtower, 4D Intelligence) are intentional canonical positioning. Selective plain-English subtitles/tooltips are a reasonable future enhancement; wholesale de-jargoning would dilute the brand. Left.
23 | Inconsistency | About Page vs Homepage | About Page Says 3 Countries - Homepage Claims Global | MEDIUM | The footer says Global - All currencies suggesting worldwide availability. But the About page states only 3 Countries Active. These two signals are contradictory and create trust confusion for prospective buyers outside the 3 active markets. | Footer: Global label. About page: 3 Countries Active stat. | Either update the footer Global label to something more precise (e.g. Available in 15+ countries) or update the About page stat to reflect genuine global availability. Align these two data points. | Fixed | Per founder ('globally ready — 3 countries undermines'): changed the stat '3 / Countries Active' -> '22 / Languages' (a hard, verifiable global-readiness fact that also makes the stat row all-capability) and removed the 'Active in 3 countries' clause from the meta description + a value proof. 22 locales. Live. sundae-website PR #90 (merged to main, live on sundae.io)
24 | Inconsistency | Homepage Stat vs About Page Stat | Intelligence Modules Count Inconsistency | MEDIUM | The homepage prominently states 12 intelligence modules in the built with operators section. The About page also shows 12 INTELLIGENCE MODULES. These match but the homepage also mentions 12 data domains unified in one ledger which creates potential confusion between modules and domains being both numbered 12. | Homepage copy: 12 intelligence modules and 12 data domains. About page: 12 intelligence modules. | Clarify the distinction between modules and data domains more explicitly. Consider labelling one of the 12 figures differently to avoid user confusion between the two. | Not valid | Not an error: 12 data domains and 12 intelligence modules are architecturally distinct and both real/intentional. The numbers are correct; at most a one-line copy clarification. No change.
25 | Accessibility | Site-Wide | Low Contrast Text on Dark Gradient Backgrounds | MEDIUM | Multiple pages use medium-grey body text on near-black backgrounds. Radial gradient decorations behind text sections worsen contrast. Likely below WCAG AA 4.5:1 in several places. | Observed across dark background text sections on all pages | Run all colour combinations through WCAG contrast checker. Increase minimum body grey to #ADADAD or brighter on dark backgrounds. Avoid body copy over gradient backgrounds. | Fixed (targeted) | Computed contrast: body text passes AA (secondary ~10:1, muted ~5.4:1); only --text-faint (~1.6:1) fails, and it is mostly decorative (aria-hidden separators). Lifted the READABLE text-faint labels (footer category labels + timeline axis labels) to AA-passing --text-muted; left decorative separators. sundae-website PR #90 (merged to main, live on sundae.io)
26 | Accessibility | Site-Wide | Hamburger Menu Button Has No Visible Label | LOW | The hamburger icon has no visible text label and presumably no aria-label. Screen reader users will encounter an unlabelled interactive element. | Hamburger button top-right on all pages | Add aria-label=Open navigation menu to the button. Change to Close navigation menu and aria-expanded=true when open. | Not valid | Already correct: the hamburger button already has aria-label (toggling Open/Close menu) + aria-expanded — exactly what the auditor 'recommended.' The auditor hedged ('presumably no aria-label') — a wrong guess. No change.
27 | UX - Content | Homepage | Interactive Scrubber Has No Visual Affordance | LOW | The Drag to scrub the night timeline element is innovative but has no drag-handle icon or animation hint. Most users will scroll past it without realising it is interactive. | Homepage service-night timeline section | Add an auto-animation on page load that nudges the thumb left-right. Add a drag-handle icon and tooltip: Drag to replay the shift. | Left (partly invalid) | Premise partly wrong: the timeline already has a 'Drag to scrub the night' hint + play/pause/replay transport controls. An extra auto-nudge animation is a minor optional enhancement (not done). Its labels did receive the row-25 contrast lift.
28 | UX - Positive | Site-Wide | Strong Visual Design and Brand Identity | POSITIVE | Distinctive premium aesthetic. Dark background, serif typography, warm amber/terracotta accents, and high-quality restaurant photography create a cohesive and memorable brand that stands apart from generic SaaS competitors. | Consistent across all page screenshots throughout audit | Maintain this design language as a competitive differentiator. Ensure pricing subdomain and app login are updated to fully match this visual identity. | Acknowledged | Agreed — the premium warm-signature identity is a differentiator. Maintained; this pass brought the pricing subdomain + cookie chrome into full parity. sundae-pricing PR #18 (merged to main, deploying to pricing.sundae.io)
29 | UX - Positive | Site-Wide | No Spelling Errors Found in Page Copy | POSITIVE | All publicly visible copy across product pages, solutions pages, hero sections, and footers was grammatically correct and spelling error-free (with the exception of the broken sentence on the Crew page noted separately in row 14). | All pages audited during session | Maintain quality copywriting standard. Add a copy review step to the pre-publish QA checklist. | Acknowledged | Agreed. The one exception (the Crew hero) was fixed — see row 14. i18n + copy QA gates enforce quality on every build.
30 | UX - Positive | Homepage | Signal Cards on Homepage Are Highly Effective | POSITIVE | The Floor / Pass / Room signal cards with View Signal interactions give a concrete, vivid demonstration of the product in action. These are the clearest and most compelling product communication elements on the entire site. | Homepage signal card section | Consider bringing a version of these signal cards into individual product pages for Pulse, Watchtower, and Insights to maintain the same clarity further down the funnel. | Acknowledged | Agreed — the Floor/Pass/Room signal cards are the clearest product communication on the site. The suggestion to reuse them on the Pulse/Watchtower/Insights product pages is noted for a future pass (not done this round).